## Sheet1
Network information:
Operational LAN System
[6 empty] | Activity Description Preceding Activity Activity time | [9 empty] | Cirtical path
[6 empty] | A server with dual core processor |  | Purchase Servers with dual processors | [5 empty] | 1 week |  | ✓
[6 empty] | B | Purchase workstation and laptop computers |  |  |  |  | A |  | 1 |  | ✓
[6 empty] | C | Purchase printers |  |  |  |  | A |  | 1 |  | ✓
[6 empty] | D | Purchase Workstation operating system |  |  |  |  | B |  | 1 |  | ✓
[6 empty] | E | Purchase Windows R2 server |  |  |  |  | B |  | 1 |  | ✓
[6 empty] | F | migrate of database and program |  |  |  |  | C |  | 2 |  | ✓
[6 empty] | G | training for client network administrator |  |  |  |  | D |  | 1 |  | ✓
[6 empty] | H | introduction training for client personnel |  |  |  |  | E |  | 1 |  | ✓
[6 empty] | I | operational LAN system F,G,H |  |  |  |  | F,G,H |  | 2 |  | ✓
|  |  | 1 | C | 2 |  |  |  | 2 | F | 4
|  |  | 0 | Purchase printers |  |  |  |  | 0 | migrate Database
|  |  | 1 | 1 | 2 |  |  |  | 2 | 2 | 4
0 | A | 1
0 | Purchase Servers | [5 empty] | 2 | E | 3 |  | 3 | H | 4
0 | 1 | 1 |  |  |  |  | 0 | P windows server |  |  | 0 | introduction for client
[7 empty] | 2 | 1 | 3 |  | 3 | 1 | 4 |  | 4 | I | 6
[15 empty] | 0 | LAN system
|  |  | 1 | B | 2 | [9 empty] | 4 | 2 | 6
|  |  | 0 | P workstation and laptops
|  |  | 1 | 1 | 2
[7 empty] | 2 | D | 3 |  | 3 | G | 4
[7 empty] | 0 | P workstation OS |  |  | 0 | Training client admin
[7 empty] | 2 | 1 | 3 |  | 3 | 1 | 4