|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Task Name | Duration | Start | Finish | Predecessors | Free Slack | Total Slack |
| **LAN system** | **42 days** | **أ 20/01/21** | **خ 18/03/21** |  | **0 days** | **0 days** |
| Purchase Servers | 7 days | أ 20/01/21 | خ 28/01/21 |  | 0 days | 0 days |
| Purchase workstation and laptop computers | 7 days | ج 29/01/21 | إ 08/02/21 | 2 | 0 days | 0 days |
| Purchase printer | 7 days | ج 29/01/21 | إ 08/02/21 | 2 | 0 days | 0 days |
| Purchase windwos R2 server | 7 days | ث 09/02/21 | أ 17/02/21 | 3 | 0 days | 0 days |
| Purchase workstation operation system | 7 days | ث 09/02/21 | أ 17/02/21 | 3 | 0 days | 0 days |
| Migrate of existing database and program | 14 days | ث 09/02/21 | ج 26/02/21 | 4 | 0 days | 0 days |
| Training for client network administrator | 7 days | خ 18/02/21 | ج 26/02/21 | 5 | 0 days | 0 days |
| Introduction training for client personal | 7 days | خ 18/02/21 | ج 26/02/21 | 6 | 0 days | 0 days |
| Fully operational LAN system | 14 days | إ 01/03/21 | خ 18/03/21 | 7;8;9 | 0 days | 0 days |

